## Sheet1
SEVERITY
SEVERITY
| Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level |  |  |  | Minimal | Minor | Moderate | Major | Severe
1 | Too many users access the App | Server Crashes - overloads | Add more workers in Gunicorn | Make sure app can handle expected load | Likely | Major | 12 |  | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | Data Corruption | Users lose their saved characters | Re-Upload the database | Create database backups that can be used as restore points | Expected | Moderate | 12 |  |  | Expected | 4 | 8 | 12 | 16 | 20
3 | Typo/human error | mis-spelt items/incorrect | check all inputs | Validating inputs | Possible | Minimal | 2 |  |  | Likely | 3 | 6 | 9 | 12 | 15
4 | Older versions of the code online may open up the possibility of a data breach | User information is leaked, databases are compromised | Check all repo versions for sensitive information | No security information online | Possible | Major | 8 |  |  | Possible | 2 | 4 | 6 | 8 | 10
5 | GCP Outage | Users unable to access information | Look into alternative hosting | 24/7 uptime | Unlikely | Moderate | 3 |  |  | Unlikely | 1 | 2 | 3 | 4 | 5